## Content
Version: 1.1
Instructions
Project Information
Release Plan
Product Burndown
Document Control
Release, Iteration Burndown
Product Backlog
Release, Iteration Backlog
Prioritize features using WSJF

## Instructions
Instructions
| Project Information | Basic information about the project
| Weighted Shortest Job First (WSJF) | An approach to prioritize features for Optimal ROI. This tab provides the approach and formula for prioriting using WSFJ; can be used for prioritizing Features or Epics.
| Release Plan | Date-driven release plan template. You can document the release plan here or using indidual Release Plan-Agile template. Multiply the velocity by the number of iterations to calculate the total work that can be completed within the release timeline.
| Product Backlog | Refer to cell comments in headers 'Business Value' and 'Priority' for inputs on identifying business value and priority for the stories.
| Release and Iteration Backlog | Provides release backlog for 4 iterations and iteration (sprint) backlog for 10 days iteration. For longer iteration/sprint, insert required number of columns in between iteration and update formulae. For release(s) of >4 iterations: > copy all 10 columns of an iteration and insert in between two iterations > update formulae for estimation hours for new range of data (formula in cell J8 & onwards) For more stories: > insert required number of rows > update cell I8 (estimated/planned effort) for release scope > update sum range in cells I9, S9, AC9, ....etc. for iteration scope
| Product Burndown | Green bars tracks the remaining Product Backlog story points from one iteration to the next. The intersection point where Max(green) line and Min(amber) line meet is the predicted iteration when the release will be completed.
Back to Content

## Prj_Info
Project Information
Project Name/Subproject Name:
Project Manager:
Iteration Manager (Scrum Master):
Project ID/ Subproject ID:
Document Type/Title:
| Confidentiality: | <Confidential, N/A, etc.>
| Template version: | <1.0>
Back to Content

## WSJF
Prioritizing features for Optimal ROI
1. Calculate:
a. Cost of Delay (CoD) in delivering value for the feature
b. Duration to implement the feature
2. Prioritize the Shorted Job, when CoD is equal | Feature | Duration to implement | Cost of Delay
| F1 | 2 | 4
| F2 | 5 | 4
| F3 | 8 | 4
3. Prioritize Highest CoD, when duration is equal | Feature | Duration to implement | Cost of Delay
| F1 | 5 | 9
| F2 | 5 | 5
| F3 | 5 | 3
4. Prioritize using Weighted Shortest Job First (WSJF) when nothing is equal | Feature | Duration to implement | Cost of Delay | Weight = CoD/Duration
| F1 | 5 | 3 | 0.6
| F2 | 2 | 10 | 5
| F3 | 3 | 9 | 3
Note: You can use job size if duration is unknown.
WSJF stakeholders: Business Owners, Product Managers, Product Owners, System Architects
Cost of Delay User-Business Value + Time Criticality + RROE Value
WSJF = =
Duration or Job Size Duration or Job Size
Back to Content
Elements of Cost of Delay
A. User and Business Value (Relative value to the customer or business):
  - Is this feature preferred over other?
  - What is the revenue impact?
  - Is there potential penalty or other negative impact?
B. Time Criticality (How User Business Value decays over time):
  - Is there a fixed deadline?
  - Will they wait for feature completion or move to another solution?
  - What is the current effect on customer satisfaction?
C. Risk Reduction & Opportunity Enablement-RROE (What other values does this feature brings for the business):
  - Reduces the risk of current or future delivery?
  - Is there value in the information which will be received?
  - Enables new business opportunities?
  - Etc.

## Release Plan
Release Plan
Project/Work Order No.:
Release Goal: Release every iteration of length <n> weeks
Release Scope (User Story Nos.) | User Story description | Estimation for release (total story points) | Priority | Release <number> | Release start date | Deployment/ Go Live Target date (if applicable)
e.g.
5 | As an unauthorised user I want to create a new account | 3 | 1
2 | As an unauthorised user I want to login | 2 | 2
8 | As an authorised users I want to logout | 2 | 3
….. | …….. | ……. | …….
….. | …….. | ……. | …….
Team velocity: < ..> story points/ iteration
Back to Content

## Product Backlog
Product Backlog
refer
ID | Release | Theme/ Feature | As a/an …. I want to……. so that……. | Acceptance Criteria | Business Value | Priority | Initial Story Points Estimated | Revised Story Points | Story Points Remaining | Status | Added in Iteration | Revised in Iteration | Closed in Iteration
1 | X.X1 |  | create a profile |  |  | 1 | 30 |  |  | Completed | 1 |  | 1
2 | X.X1 |  | create a wish list of the products I intend to buy in near or long term futue |  |  | 2 | 30 |  |  | In Progress | 1 |  | 1
3 | X.X2 |  | be able to register for an account |  |  | 5 | 50 |  |  | Not Started | 2 |  | 2
3 | X.X2 |  | be able to post the details of my products |  |  | 4 | 60 |  |  | In Progress | 2 | 2 | 3
4 | X.X3 |  | be able to register for an account |  |  | 3 | 10 |  |  | Completed | 3 |  | 3
Back to Content
Note on F3: Points to consider to identify BV: User and Business Value (Relative value to the customer or business): - Is this feature preferred over other? - What is the revenue impact? - Is there potential penalty or other negative impact?
Note on G3: Refer to WSJF (Weighted Shortest Job First) tab for prioritizing

## Release_Iteration Backlog
Release, Iteration Backlog
Release number: | [5 empty] | Release date: dd/mmm/yy - dd/mmm/yy |  |  |  |  | Iteration number: 1 | [9 empty] | Iteration number: 2 | [9 empty] | Iteration number: 3 | [9 empty] | Iteration number: 4
Release Goal: | [10 empty] | Iteration date: dd/mmm/yy - dd/mmm/yy | [9 empty] | Iteration date: dd/mmm/yy - dd/mmm/yy | [9 empty] | Iteration date: dd/mmm/yy - dd/mmm/yy | [9 empty] | Iteration date: dd/mmm/yy - dd/mmm/yy
[11 empty] | Iteration Goal: | [9 empty] | Iteration Goal: | [9 empty] | Iteration Goal: | [9 empty] | Iteration Goal:
[9 empty] | Day -> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
[9 empty] | Update this planned/estimated hours formula range for the release scope -> | 58 | 56.4737 | 54.9875 | 53.5014 | 52.0152 | 50.5291 | 49.0429 | 47.5568 | 46.0706 | 44.5845 | 43.0983 | 41.6122 | 40.126 | 38.6399 | 37.1537 | 35.6676 | 34.1814 | 32.6953 | 31.2091 | 29.723 | 28.2368 | 26.7507 | 25.2645 | 23.7784 | 22.2922 | 20.8061 | 19.3199 | 17.8338 | 16.3476 | 14.8615 | 13.3753 | 11.8892 | 10.403 | 8.9169 | 7.4307 | 5.9446 | 4.4584 | 2.9723 | 1.4861 | 0
[9 empty] | Update this planned/estimated hours formula range for the iteration scope -> | 58 | 51.5556 | 45.1111 | 38.6667 | 32.2222 | 25.7778 | 19.3333 | 12.8889 | 6.4444 | 0 | 58 | 51.5556 | 45.1111 | 38.6667 | 32.2222 | 25.7778 | 19.3333 | 12.8889 | 6.4444 | 0 | 58 | 51.5556 | 45.1111 | 38.6667 | 32.2222 | 25.7778 | 19.3333 | 12.8889 | 6.4444 | 0 | 58 | 51.5556 | 45.1111 | 38.6667 | 32.2222 | 25.7778 | 19.3333 | 12.8889 | 6.4444 | 0
[9 empty] | Remaining effort -> | 58 | 45 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 35 | 21 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 31 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 31 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Epic/ Feature ID | User Story | Story Point | Revised story points | Iteration number | Task ID | Task | Priority | Estimated hours | Task Resp. (resource name) | Taskwise remaining effort | [9 empty] | Taskwise remaining effort | [9 empty] | Taskwise remaining effort | [9 empty] | Taskwise remaining effort
| User story 1 | 10 | 10 |  | Task 1 | 1 |  | 4 | Name | 4 | 0 | 0 | [7 empty] | 4 | 0 | 0 | 0 | [6 empty] | 4 | 0 | 0 | [7 empty] | 4 | 0 | 0
[5 empty] | Task 2 | 2 |  | 8 | Name | 8 | 6 | 4 | [7 empty] | 8 | 0 | 0 | 0 | [6 empty] | 8 | 0 | 0 | [7 empty] | 8 | 0 | 0
[5 empty] | Task 3 | 5 |  | 6 | Name | 6 | 6 | 5 | [7 empty] | 6 | 6 | 5 | 0 | [6 empty] | 6 | 6 | 5 | [7 empty] | 6 | 6 | 5
[5 empty] | Task 4 | 4 |  | 4 | Name | 4 | 4 | 0 | [7 empty] | 4 | 4 | 0 | 0 | [6 empty] | 4 | 4 | 0 | [7 empty] | 4 | 4 | 0
[5 empty] | Task 5 | 5 |  | 6 | Name | 6 | 4 | 4 | [7 empty] | 6 | 8 | 0 | 0 | [6 empty] | 6 | 4 | 0 | [7 empty] | 6 | 4 | 0
[5 empty] | Task 6 | 6 |  | 8 | Name | 8 | 8 | 8 | [7 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
[5 empty] | Task 7 | 7 |  | 4 | Name | 4 | 4 | 0 | [7 empty] | 4 | 4 | 5 | 5 | [6 empty] | 4 | 4 | 0 | [7 empty] | 4 | 4 | 0
[5 empty] | Task 8 | 8 |  | 8 | Name | 8 | 3 | 1 | [7 empty] | 8 | 3 | 1 | 1 | [6 empty] | 8 | 3 | 1 | [7 empty] | 8 | 3 | 1
[5 empty] | Task 9 | 9 |  | 6 | Name | 6 | 6 | 0 | [7 empty] | 6 | 6 | 6 | 0 | [6 empty] | 6 | 6 | 0 | [7 empty] | 6 | 6 | 0
[5 empty] | Task 10 | 10 |  | 4 | Name | 4 | 4 | 4 | [7 empty] | 4 | 4 | 4 | 0 | [6 empty] | 4 | 4 | 4 | [7 empty] | 4 | 4 | 4
| User Story 2 | 10 | 10 |  | Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
Task 7
Task 8
Task 9
Task 10
Task 11
| User Story 3 | 12 | 12 |  | Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
Task 7
Task 8
Task 9
| User Story 4 | 5 | 5 |  | Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
| User Story 5 | 5 | 5 |  | Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
Task 7
Task 8
User Story 6
User Story 7
User Story 8
User Story 9
User Story 10
User Story 11
User Story 12
User Story 13
User Story 14
User Story 15
Back to Content
Release Burndown
Iteration Burndown
Iteration Burndown
Iteration Burndown
Iteration Burndown
Note on AO7: For more iterations, copy all 10 columns and insert between 2 iterations.
Note on U9: Update range
Note on AE9: Update range
Note on AO9: Update range
Note on B128: For more stories, insert rows in between stories.

## Product Burndown
Product Burndown
Iteration/ Sprint | Story Points Completed | Story Points Remaining | Scope Change (in story points) | Cumulative Story Points Done | Cumulative scope change | Min. | Max. | Velocity
1 | 20 | 120 | 0 | 20 | 0 | 0 | 120 | 20
2 | 10 | 110 | 3 | 30 | 3 | -3 | 107 | 10
3 | 21 | 110 | 2 | 51 | 5 | -5 | 105 | 21
4 | 14 | 90 | 0 | 65 | 5 | -5 | 85 | 14
5 | 22 | 80 | 4 | 87 | 9 | -9 | 71 | 22
6 | 15 | 75 | 6 | 102 | 15 | -15 | 60 | 15
7 | 17 | 60 | 2 | 119 | 17 | -17 | 43 | 17
8 | 9 | 40 | 1 | 128 | 18 | -18 | 22 | 9
9 | 18 | 20 | 0 | 146 | 18 | -18 | 2 | 18
10 | 20 | 0 | 5 | 166 | 23 | -23 | -23 | 20
Back to Content

## Release_Iteration Burndown
Release, Iteration Burndown
Back to Content
Release, Iteration Backlog

## Doc Control
Document Control
Project Tracker Template - Revision History
Version Number | Revision Date | Change Description | Changed Name | Business Need reference
1 | May-2016 | Initial version | GBS Process Capability team | BNs - 485, 487, 488
1.1 | 2016-07-01 | Refined Release Plan, Product Backlog and Iteration Backlog worksheets. | GBS Process Capability team | MI -1145
Back to Content