## Slide 1: EDR Blockchain Communication Campaign Roadmap
Draft for discussion
October 2017
Notes: When the draft media vlogs will be launched
Wish well in the beginning
-social media
-the look of government doing something different
-vehicle to talk to communications at OPM (Marcel to engage with POC)
-IBM site for EDR
-blockchain working group?
-Congressional BC pocket
-Digital Chamber of Commerce – March Annual Form (Georgetown)
Government Wide Lessons Learned
Think Conference – present
Data Transparency Group Conferences (Hudson)
Center of Excellence Conference (Lynn)
Booz Allen Internal Project of the Year for IBM (what do we need to do to get the list, Best of IBM – Project of Year, Public Sector) -Raiza
Federal Government Awards ( does the prototype count for that kind of recognition) FCW GTN

## Slide 2: EDR Blockchain Communication Campaign Roadmap
Oct 17
Nov 17
Dec 17
Jan 18
Feb 18
Mar 18
Awareness
Interest
Consideration
Intent
Evaluation
Action
Stakeholders
logo +
style guide
Website
Creation
Social media
Strategy
Design Thinking
Workshops
Email
Campaign
Social media
Profile creation
To-be case
study written
Case-study
socialization
Ongoing Stakeholder Meetings
Ongoing Social Media Engagement
Demo transcript
created
Informational
video created
Demos
Demo video
created
Demo one
pager
Final presentation
Deck
IRB
Members
CHCOs
Demo Business
Network Members
OPM CIO
IRB
Members
CHCOs
Demo Business
Network Members
OPM CIO
IRB
Members
IRB
Members
IRB
Members
IRB
Members
CHCOs
Demo Business
Network Members
Demo Business
Network Members
Engage with:
Federal Computer Weekly
Federal News Radio
Government Computer News
Meritalk
Bloomberg BNA
Human Capital Working Group Biweekly Meetings
Human Capital
Working Group
Kickoff
Notes: When the draft media vlogs will be launched
Wish well in the beginning
-social media
-the look of government doing something different
-vehicle to talk to communications at OPM (Marcel to engage with POC)
-IBM site for EDR
-blockchain working group?
-Congressional BC pocket
-Digital Chamber of Commerce – March Annual Form (Georgetown)
Government Wide Lessons Learned
Think Conference – present
Data Transparency Group Conferences (Hudson)
Center of Excellence Conference (Lynn)
Booz Allen Internal Project of the Year for IBM (what do we need to do to get the list, Best of IBM – Project of Year, Public Sector) -Raiza
Federal Government Awards ( does the prototype count for that kind of recognition) FCW GTN